## Cover Sheet
Action Plan
Actions have been added related to different areas of the organisation and buildings(s). Please click on the tabs at the bottom to access the different area actions. Actions have been listed under years in each case, with implementation dates within each year There are additional columns included, in order for the organisation's management team to be able to track progress and make other notes where required Graphs showing the organisation's current (baseline) emissions are included, along with any savings that PECT have calculated. *Please add a new line for each action to address - REMOVE BEFORE SENDING TO ORG
Signed by managament annually - Signed 01/09/2025
Jenny Hodson John Hodson
Accuracy of imformation
PECT is committed to providing accurate information. However, the savings calculations referenced in this document make assumptions based on the data and information provided by the client and other external sources.
Any assumptions made are detailed in the Roadmap document that accompanies this action plan
Assumptions, Caveats & Calculations
· Building use has been estimated using the opening and closing times provided by the organisation.
· All data has been provided remotely by the beneficiary. Change if site visit
· All calculations are based on annual utility usage provided by the organisation, unless otherwise stated. Data provided has not been 3rd party verified.
· Where verifiable data is not available, a pro-rata extrapolation method has been used to estimate the data. This means using figures from another comparable time period to fill the gap.
· The Emissions Statements presented in this document include the key energy emission sources for which the organisation has provided data. An emissions statement is a means of expressing the environmental impact of resource consumption and is presented as tonnes of carbon dioxide equivalent (tCO2e) to account for the impacts of all seven Kyoto Protocol gases. Both current and predicted Emissions calculations use Defra’s most recently published Greenhouse Gas Conversion Factors conversion factors (June 2023). https://www.gov.uk/government/publications/greenhouse-gas-reporting-conversion-factors-2023
· Emission sources have been categorised according to the World Resources Institute’s (WRI’s) greenhouse gas protocol methodology - https://ghgprotocol.org/sites/default/files/standards/ghg-protocol-revised.pdf
· With regard to Scope 2 emissions, we have used the location-based methodology as outlined in the GHG Protocol. Under this methodology, all emissions are reported using standard emissions factors as released by the UK Government annually. https://ghgprotocol.org/sites/default/files/Scope2_ExecSum_Final.pdf
· This document focusses on Scope 1 & 2 emissions, based on data provided by the organisation, and Scope 3 emissions have been considered only where deemed material and where the information has been provided to us.
· Current GHG Protocols for reporting scope 2 location based emissions require us to quote the usual scope 2 emissions for electricity supply for green tariffs. Consequently, emissions will be reported calculated as usual for electricity usage.
· Any claims made regarding emissions and / or costs savings in the future are dependent on the organisation implementing the improvements suggested in this document and we understand that priorities may change based on business performance and priorities.

## Energy Usage
|  | Analysis |  |  | Action |  |  | Implementation
Building Name | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | Predicted CO2 saving | Implementation Start Date | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Main Building | 2 | Electricity supply | Electricity usage | Install localised Smart monitoring for different areas of the building | Invest in plug-in smart monitors | High |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Main Building | 2 | Electricity supply | Electricity production | Fit additional panels to existing solar PV system | invest in 40 additional solar panels | High |  | 2025-01-02 | Jenny Hodson | 2025-01-21 | Progress/status reviewed in monthly management meeting | ü
Main Building | 2 | Electricity supply | Electricity production | Investigate wind power as a renewable source wind turbines | Investigate a wind turbine solution | High |  | 2024-09-01 | John Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Main Building | 2 | Electricity supply | Electricity production | Upgrade inverter to allow additional solar panels and wind turbines to existing system | Contact supplier (Cambridge Solar) to obtain options for upgrading the inverter | High |  | 2025-01-02 | Jenny Hodson | 2025-01-21 | Progress/status reviewed in monthly management meeting | ü
Main Building | 2 | Electricity supply | Electricity production | Install several wind turbines to assess generation figures | Investigate a wind turbine solution | Low |  | 2024-09-01 | John Hodson | 2025-01-15 | Progress/status reviewed in monthly management meeting | ü
Main Building | 2 | Equipment | Electricity usage | Monitor the energy used by individual equipment | Invest in plug-in smart monitors | High |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole Organisation | 2 | Equipment | Usage | Ensure all equipment is switched off when not in use | Produce signage for all equipment around the site | High |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole Organisation | 2 | Equipment | Usage | Ensure all equipment is switched off outside of working hours | Produce signage for all equipment around the site | High |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Year 2
Main Building | 1 | Equipment | Electricity usage | Install new, more energy efficient printer | Research options and attend demos, finally making purchase and manage installation including reinforcement to print room flooring. | High |  | 2025-03-01 | Jenny Hodson | 2025-04-30 | Progress/status reviewed in monthly management meeting
Main Building | 2 | Electricity supply | Electricity production | Install Infrared heating system to replace oil heating in workshop | Research options and have a sit survery conducted to assess energy savings and site suitability. Purchase and order installation. | High |  |  |  |  | Progress/status reviewed in monthly management meeting
Year 3
Main Building | 2 | Electricity supply | Electricity production | Install infrared heating system in offices subject to workshop heaters being both efficient and effective
Year 4
Main Building | 2 | Electricity supply | Electricity production | Fit solar to new building
Main Building | 1
Main Building | 2 | Electricity supply | Electricity production | Install further wind turbines
Year 5

## Building
|  | Analysis |  |  | Action |  |  | Implementation
Building Name | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | Predicted CO2 Saving | ImplementationStart Date | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Main Building | 1 | Fabric of the Bulding | Windows | Fit heat reflective blinds/curtains in office space | Fit blinds | Low |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting
Year 2
Year 3
Year 4
Year 5

## Transport
|  | Analysis |  |  | Action |  |  | Implementation
Building Name | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | Predicted CO2 saving | Implementation Start Date | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Main Building | 1 | Indirect Transport | Commuting | Monitor how staff travel for business purposes | Vehicle sharing as standard | High |  | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Main Building | 1 | Indirect Transport | Commuting | Homeworking where appropriate to reduce travel to work | In place where appropriate | Low |  | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Main Building | 1 | Indirect Transport | Commuting | Encourage car sharing amongst staff to reduce individual car use | In place where appropriate | Low |  | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Main Building | 1 | Indirect Transport | Commuting | Introduce a Cycle to Work Scheme | Set-up scheme | High |  | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Year 2
Logistics | 1 | Direct transport | Logistics | Purchase BE Vans | Shop around, research payload and vehicle range | High |  | 2025-04-01 | Jenny Hodson | 2025-06-01 | Progress/status reviewed in monthly management meeting | ü
Logistics | 3 | Indirect Transport | Logistics | Start analysing mileage data for customer deliveries to identify possible changes that can be made
Logistics | 1 | Direct transport | Logistics | Install Bio-Fuel Pump at GH Display | Purchase, prep site and arrange installation | High |  | 2024-02-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Logistics | 1 | Direct transport | Logistics | Move all diesel vehicles onto Bio-fuel (Hydrotreated Vegetable Oil) | Purchase, prep site and arrange installation | High |  | 2024-02-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Year 3
Logistics | 1 | Indirect Transport | Logistics | Capture emissions / mileage data for incoming supplies (to the business address)
Logistics | 3 | Indirect Transport | Logistics | Contact all suppliers and ask for their Net Zero Roadmaps / Env Sustainablity plans / strategies
|  | Direct transport | Logistics | Review logistics planning to see if BEVs could be used for some journeys
Year 4
Logistics | 1 | Direct transport | Logistics | Purchase 2 BE Vans
Whole Organisation | 1 | Direct transport |  | Replace pool car with BEV
Year 5
Logistics | 1 | Direct transport | Logistics | Purchase 2 BE Vans

## Water
|  | Analysis |  |  | Action |  | Implementation
Building Name | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | ImplementationStart Date | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Main Building | 3 | Water | Usage | Fit low flow taps | Request plumbing job where practical | Low | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting | On-hold due to new toilet facilcities being fitted.
Main Building | 3 | Water | Sewerage | Fit water reduction device to toilet | Request plumbing job where practical | Low | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting | On-hold due to new toilet facilcities being fitted.
Main Building | 3 | Water | Usage | Fit Water sensor taps or time limited taps | Request plumbing job where practical | Low | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting | On-hold due to new toilet facilcities being fitted.
Main Building | 3 | Water | Usage | Reduce water (and energy) usage by not overfilling kettles etc | Install sign in both kitchens | High | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting | ü
Year 2
Year 3
Year 4
Main Building | 3 | Water | Usage | Investigate grey water systems

## Waste
|  | Analysis |  |  | Action |  | Implementation
Building Name | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | ImplementationStart Date | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Whole Organisation | 3 | Waste & Recycling | Monitoring | Begin to measure waste amounts (Timber,mdf, plastics, and general) | Implement a waste measuring process | High | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting
Whole Organisation | 3 | Waste & Recycling | Reduction | Reduce all waste creation where possible | Continue with reuse, recylcle and refubish of manufacturered products | High | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monhtly management meeting | NA
Whole Organisation | 3 | Waste & Recycling | Reuse | Looking for opportunities for the reuse of waste | Continue with reuse, recylcle and refubish of manufacturered products | High | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monhtly management meeting | NA
Whole Organisation | 3 | Waste & Recycling | Recycle | Invest in products that are readily recylable | Continue with reuse, recylcle and refubish of manufacturered products | High | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monhtly management meeting | NA
Whole Organisation | 3 | Waste & Recycling | Waste in manufacturing processes | Review all processes to look for waste reduction opportunities | Company wide review of processes | High | 2024-09-01 | Jenny Hodson | Ongoing | Progress/status reviewed in monhtly management meeting | NA
Year 2
Whole Organisation | 3 | Waste & Recycling | Recycled material useage | Re-review print media market to find better recycled media products, since stretch issues with existing recycled marine waste medias | Find and test new product options | High | 2025-09-01 | Jenny Hodson | 2025-12-30 | Progress/status reviewed in monhtly management meeting
Year 3
Year 4
Year 5

## Staff Projects - Governance
|  | Analysis |  |  | Action
Area | Scope | Emissions Area | Specific issue | Goals and Targets | Actions to Address | Priority | Responsible person | Target Timeframe for Completion | How this action will be measured/monitored | Tick when Complete where applicable (note: not all actions will have a natural end date and may be ongoing)
Year 1
Whole organisation | 1 | Energy consumption | Monitoring of energy consumption | Get half hour data from your smartmeters and check for hotspots / take daily / weekly / monthly energy readings and record | Review current smart metre set-up | High | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Whole organisation | All | Embedding Net Zero | Cloud storage | Reduce amount of cloud storage or move to a supplier that uses renewable energy to power server systems | Review current set-up | High | John Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Reviewing | Add Net-zero action plan to all management meeting agendas and update regularly with progress | Added to all management meetings | High | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Whole organisation | All | Embedding Net Zero | Green Champions | Appoint a Green Champion to be responsible for sustainability/energy management | Appointed | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Staff training | Organise relevant training for the team | 4 team members booked on ESSA Sustainabilty Training Day 05/11/24 | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Staff training | Add Net Zero training to induction processes and procedures | Review options | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Target setting | Review sustainability objectives/goals in the 5 year Net Zero plan | Review each year in our sustainability policy | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Strategic Planning | Add sustainability actions and targets to your strategic business plan and update regularly | This document to be reviewed in monthly management meetings | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Green accreditation | Look into accreditions for Green certification | Applying for sustainablility accrediation through ESSA | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Environmental Sustainability policy | Review and update your policy | Scheduled annually | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | 3 | Embedding Net Zero | Sustainable procurement policy | Create a policy with Net Zero activities, obtaining advice where necessary | Exists as part of our sustainability policy | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | 3 | Travel | Environmental Sustainability travel policy | Set up / review sustainable travel policy | Exists as part of our sustainability policy | High | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting
Whole organisation |  | All | Designing environmentally sustainable processes | Review all processes to look for decarbonisation opportunities | Exists as part of our sustainability policy | High | Jenny Hodson | 2026-02-01 | Progress/status reviewed in monthly management meeting
Year 2
Whole organisation | All | Legislation and regulation | Changes to regulations / legislation | Review legislation and regulation for your industry and implement changes where required | Review new legistlation and update polciies | High | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Main Building | 1 | Energy consumption | Monitoring of energy consumption | Monitor and report energy consumption for the year | Monitor consumption | High | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Main Building | 2 | Energy consumption | Green tariff | Assess the Green Credentials of your energy provider and switch if necessary / feasible | Review the market place | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Carbon Footprint | Recalculate your carbon footprint to monitor progress | Source partner | Med | Jenny Hodson | 2026-01-01 | Progress/status reviewed in monthly management meeting
Main Building | All | Embedding Net Zero | Cloud storage | Report on cloud storage emissions for the year and any actions taken to reduce | Research solutions | Med | Jenny Hodson | 2026-01-01 | Progress/status reviewed in monthly management meeting
Whole organisation | All | Embedding Net Zero | Auditing | Carry out Net Zero audits for the whole organisation | Source partner | Med | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Whole organisation | All | Embedding Net Zero | Staff training | Organise relevant update training for the team | Source relevant training providers | Med | Jenny Hodson | Ongoing | Progress/status reviewed in monthly management meeting | NA
Whole organisation | All | Embedding Net Zero | Target setting | Review sustainability objectives/goals in the 5 year Net Zero plan | Ongoing review | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Strategic Planning | Update sustainability actions and targets in your strategic business plan | Ongoing review | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | All | Embedding Net Zero | Environmental Sustainability policy | Review and update your policy | Ongoing review | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | 3 | Embedding Net Zero | Sustainable procurement policy | Review and update your policy | Ongoing review | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Whole organisation | 3 | Travel | Sustainable travel policy | Review and update policy | Not yet in place | High | Jenny Hodson | 2026-01-01 | Progress/status reviewed in monthly management meeting
Whole organisation | 3 | Logistics | Supplier management policy | Review and update policy | Not yet in place | High | Jenny Hodson | 2026-01-01 | Progress/status reviewed in monthly management meeting
Whole organisation | All | Processes | Designing environmantally sustainable processes | Review all proceses to ensure Net Zero principles are being embedded | Ongoing review | High | Jenny Hodson | 2025-01-01 | Progress/status reviewed in monthly management meeting | ü
Year 3
Whole organisation | All | Legislation and regulation | Changes to regulations / legislation | Review legislation and regulation for your industry and implement changes where required
Main Building | 1 | Energy consumption | Monitoring of energy consumption | Monitor and report energy consumption for the year
Main Building | 2 | Energy consumption | Green tariff | Assess the Green Credentials of your energy provider and switch if necessary / feasible
Whole organisation | All | Embedding Net Zero | Carbon Footprint | Recalculate your carbon footprint to monitor progress
Main Building | All | Embedding Net Zero | Cloud storage | Report on cloud storage emissions for the year and any actions taken to reduce
Whole organisation | All | Embedding Net Zero | Auditing | Carry out Net Zero audits for the whole organisation
Whole organisation | All | Embedding Net Zero | Staff training | Organise relevant update training for the team
Whole organisation | All | Embedding Net Zero | Target setting | Review sustainability objectives/goals in the 5 year Net Zero plan
Whole organisation | All | Embedding Net Zero | Strategic Planning | Update sustainability actions and targets in your strategic business plan
Whole organisation | All | Embedding Net Zero | Environmental Sustainability policy | Review and update your policy
Whole organisation | 3 | Embedding Net Zero | Sustainable procurement policy | Review policy and update policy
Whole organisation | 3 | Travel | Sustainable travel policy | Review and update policy
Whole organisation | 3 | Logistics | Supplier management policy | Review and update policy
Whole organisation | All | Processes | Designing environmantally sustainable processes | Review all proceses to ensure Net Zero principles are being embedded
Year 4
Whole organisation | All | Legislation and regulation | Changes to regulations / legislation | Review legislation and regulation for your industry and implement changes where required
Main Building | 1 | Energy consumption | Monitoring of energy consumption | Monitor and report energy consumption for the year
Main Building | 2 | Energy consumption | Green tariff | Assess the Green Credentials of your energy provider and switch if necessary / feasible
Whole organisation | All | Embedding Net Zero | Carbon Footprint | Recalculate your carbon footprint to monitor progress
Main Building | All | Embedding Net Zero | Cloud storage | Report on cloud storage emissions for the year and any actions taken to reduce
Whole organisation | All | Embedding Net Zero | Auditing | Carry out Net Zero audits for the whole organisation
Whole organisation | All | Embedding Net Zero | Staff training | Organise relevant update training for the team
Whole organisation | All | Embedding Net Zero | Target setting | Review sustainability objectives/goals in the 5 year Net Zero plan
Whole organisation | All | Embedding Net Zero | Strategic Planning | Update sustainability actions and targets in your strategic business plan
Whole organisation | All | Embedding Net Zero | Environmental Sustainability policy | Review and update your policy
Whole organisation | 3 | Embedding Net Zero | Sustainable procurement policy | Review policy and update policy
Whole organisation | 3 | Travel | Sustainable travel policy | Review and update policy
Whole organisation | 3 | Logistics | Supplier management policy | Review and update policy
Whole organisation | All | Processes | Designing environmantally sustainable processes | Review all proceses to ensure Net Zero principles are being embedded
Year 5
Whole organisation | All | Legislation and regulation | Changes to regulations / legislation | Review legislation and regulation for your industry and implement changes where required
Main Building | 1 | Energy consumption | Monitoring of energy consumption | Monitor and report energy consumption for the year
Main Building | 2 | Energy consumption | Green tariff | Assess the Green Credentials of your energy provider and switch if necessary / feasible
Whole organisation | All | Embedding Net Zero | Carbon Footprint | Recalculate your carbon footprint to monitor progress
Main Building | All | Embedding Net Zero | Cloud storage | Report on cloud storage emissions for the year and any actions taken to reduce
Whole organisation | All | Embedding Net Zero | Auditing | Carry out Net Zero audits for the whole organisation
Whole organisation | All | Embedding Net Zero | Staff training | Organise relevant update training for the team
Whole organisation | All | Embedding Net Zero | Target setting | Review sustainability objectives/goals in the 5 year Net Zero plan
Whole organisation | All | Embedding Net Zero | Strategic Planning | Update sustainability actions and targets in your strategic business plan
Whole organisation | All | Embedding Net Zero | Environmental Sustainability policy | Review and update your policy
Whole organisation | 3 | Embedding Net Zero | Sustainable procurement policy | Review policy and update policy
Whole organisation | 3 | Travel | Sustainable travel policy | Review and update policy
Whole organisation | 3 | Logistics | Supplier management policy | Review and update policy
Whole organisation | All | Processes | Designing environmantally sustainable processes | Review all proceses to ensure Net Zero principles are being embedded

## KPIs
|  | Base Lines |  | Action |  | Implementation
Building Name | Scope | Emissions Area | Suggested KPIs | Actions to address | Priority | Implementation Start Date | Responsible person | Completion/Review date | How this action will be measured/monitored
Year 1
Logistics | 1 | Direct Transport | Monitor mileage and fuel consumption |  | High | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting
Logistics | 1 | Direct Transport | Driving efficiency via telematics |  | High | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monhtly management meeting
Main Building | 2 | Electricity supply | Half hour data monitoring |  | High | 2024-09-01 | Jenny Hodson | 2025-04-01 | Progress/status reviewed in monthly management meeting
Year 2
Main Building | 3 | Manufacturing processes | Percentage of sustainable materials used | We are yet to devise a way to measure this, but will work out a way to do it accurately, | High | 2026-01-01 | Jenny Hodson | 2026-04-01 | Progress/status reviewed in monthly management meeting
Year 3
Main Building | 3 | Manufacturing processes | Monthly KPIs for manufacturing waste - quality, waste material etc
Year 4
Year 5

## Graphs & savings
Import usage and emissions graphs from Carbon Calculator spreadsheet
Please paste images
These are your Current footprint Graphs. 1. Break down of your total estimated carbon footprint. 2. The Pie chart shows you the percentage make up of your footprint. 3. The final pie chart shows you the percentage make up of your emissions by scope.
For caveats and assumptions for these savings calculations, please refer to the Roadmap Document.
Estimated current usage to heat offices (oil kWh) | Estimated new usage (electricity kWh) | Estimated savings from new heating (kWh/year) | Estimated current cost | Estimated new cost | Estimated cost saving | CO2e (t) saving
18581.3333 | 8250.112 | 10331.2213 | 1176.6976 | 1259.7921 | -83.0945 | 2.8396
Solar PV - existing roof - 20 extra solar panels - with existing battery
Possible total system size | Estimated annual generation | Estimated cost | Estimated savings from whole solar system (kWh/year) | Additional savings from extra panels | Cost savings from additional panels | Estimated payback (years) | CO2e (t) saving
70.98 | 69136.68 | 8558 | 67340.2903 | 6730.6906 | 1027.7765 | 8.3267 | 1.85
Solar PV - Adding new building - panels on east and west roofs - TO EXISTING SYSTEM + 20 ADDITIONAL PANELS
Possible additional system size (based on usage) | Estimated TOTAL annual generation | Estimated cost (March 2024) | Estimated savings from whole solar system (kWh/year) | Additional savings from extra panels | Cost savings from additional panels | Estimated payback (years) | CO2e (t) saving
47.78 | 102886.66 | 62114 | 92809 | 32199.4003 | 6484.9592 | 9.5782 | 8.8503
Existing Solar PV - 10kW battery
Current system size | Estimated annual generation | Estimated cost (March 2024) | Estimated savings from solar (kWh/year) | Estimated cost saving | Estimated payback (years) | CO2e (t) saving
63.2 | 61558.73 | N/A | 60609.5997 | 9255.0859 | N/A | 16.6591
Note on C43: Jenny Wilton: Based on £1,300 per kWp - may be cheaper as infrastructure already in place

## Data (hidden)
Priority
Low
Medium
High